## Sheet1
To be verified | Definition of passing | Date test performed | Tested by | Measured result | Passed
Accelerometer I2c functionality | 1) Read/write data from I2c registers 2) Generate an interrupt when free fall is detected. 3) Set threshold for free fall detection and free fall duration to generate interrupt when the values cross the threshold | 2021-11-17 | Sayali Mule | Verified I2C read by reading DEVID register Verified I2C write by writing value 0x08 to power measurement register and then reading it Yet to verify free fall detection | Yes
Pulse sensor I2c functionality | 1) Pulse sensor readings are within the normal pulse range(40 - 120) | 2021-11-15 | Sayali Mule | Got value around 80-100 BPM which falls under the expected range of (40 - 120) | Yes
Radio Transmit successfully | State information | 2021-11-22 | Sayali Mule | Able to send the values of BPM and free fall to client | Yes
LETimer functionality | LETimer fires every 2ms | 2021-11-20 | Sayali Mule | Verified LETIMER fires periodically using the energy profiler | Yes
Server able to bond/connect with client | Client connects to server with passkey | 2021-11-22 | Sayali Mule | Able to pair the client with server by using PB0(similar to assignment) | Yes
| Use PB0 to enable/disable Pulse sensor | 2021-11-26 | Sayali Mule | Use of PB0 to enable/disable Pulse sensor | Yes
| Use PB1 to clear previously generated free fall | 2021-11-25 | Sayali Mule | Use PB1 to clear previous free fall
LCD display | Able to display required states on LCD | 2021-12-02 | Sayali Mule | Able to display required states on LCD | yes
Low power consumption | Measure the energy consumption on energy profiler | 2021-12-04 | Sayali Mule | Able to verify the system in the low power mode(EM3) | yes
System test | Integrate the entire subsystems and test it | 2021-12-05 | Sayali Mule | Able to verify that the entire project is working fine | yes